## Sheet1
Date | Brief Description |  | Driver | Navigator | Time
2020-10-13 | Planning | Read through specification, discussed initial design and class planning. Created github repository. | N/A | N/A | 13.00-15.00
2020-10-14
2020-10-15 | Planning | Drew class diagrams, discussed the structure of the classes and the flow of the program. | N/A | N/A | 11.00-12.00
2020-10-16 | Planning | Decided on the test code that we will write. Made sure that we could both import Junit as there were some issues with this. | N/A | N/A | 14.00-15.00
2020-10-17
2020-10-18 | Test Writing | Wrote testing code for the Player, Deck and Pack class. This will make the code easier to write as we have a much clearer idea of what each method will do | Ollie | Dillon | 15.00-17.00
2020-10-19
2020-10-20 | Test Writing | Wrote the test code for CardGame. | Dillon | Ollie | 10.00-12.00
2020-10-21
2020-10-22
2020-10-23
2020-10-24 | Coding | Created a basic framework for each class. Created getter and setter methods for each, and set up attributes of the class. | Ollie | Dillon | 14.00-15.00
2020-10-25
2020-10-26 | Coding | Began adding some functionality, the code generating the decks and player hands. | Dillon | Ollie | 10.30-12.00
2020-10-27 | Coding | The code can now read the pack from a text file from a specified location. | Ollie | Dillon | 16.30-17.00
2020-10-28
2020-10-29
2020-10-30 | Coding | Added the strategy specified in the specification to the code. The game is now playable, but not yet threaded. | Dillon | Ollie | 14.00-15.00
2020-10-31
2020-11-01 | Coding | Began to thread the program, although the code could require some tweaks to make it threadable. | Ollie | Dillon | 13.00-15.00
2020-11-02
2020-11-03 | Coding | Refactored some of the code to make it able to be threaded. E.g. LinkedLists are not thread safe, and we now use a different data structure, LinkedBlockingDequeue. | Dillon | Ollie | 10.00-11.00
2020-11-04 | Coding | Finished threading the program and added writing the output to text files. | Ollie | Dillon | 14.00-16.00
2020-11-05
2020-11-06 | Report Writing | Wrote up the desgin features of the code, and how they helped us to implement our solution. | N/A | N/A | 12.00-13.00
2020-11-07 | Report Writing | Started to write the testing features up. | N/A | N/A | 14.00-15.00
2020-11-08
2020-11-09 | Report Writing | Finished writing up the test features. | N/A | N/A | 11.30-12.30
2020-11-10 | Final Code Testing | Made sure that there were no final errors in the code. Added some more comments for clarification, cleaned up the code. We then decided on the split of marks to be 50:50. | N/A | N/A | 14.00-15.30
2020-11-11
2020-11-12 | Submitted | Submitted the coursework | N/A | N/A